## Milestones
Phase | Target Month | Owner | Exit Criteria | Status
Initiation approval | May 2026 | Customer Operations Steering Committee | Charter approved and planning owner assigned. | Pending
Planning and baseline | June 2026 | Program Manager | Scope baseline, data profiling, security path, pilot cohort, and milestone plan approved. | Not Started
Design and configuration | July 2026 | Technology Owner | Dashboard design, operating model, and data feed approach accepted. | Not Started
Pilot execution | Aug-Sep 2026 | Business Owner | Pilot used by selected teams with weekly exception review and adoption tracking. | Not Started
Pilot review and handoff | Oct 2026 | Onboarding Operations | Pilot report, scale recommendation, runbook, and operational handoff completed. | Not Started

## Budget
Category | ROM Amount USD | Notes
Program management and governance | 65000 | Planning, coordination, status, steering preparation
Dashboard configuration | 140000 | Pilot dashboard build and reporting views
Data mapping and integration support | 90000 | Field mapping, extract logic, refresh validation
Security and compliance review | 35000 | Review of customer-identifiable data exposure
Pilot operations and training | 55000 | Training, runbook, adoption support
Contingency | 40000 | Must remain inside approved envelope unless sponsor approves exception
Total | 425000 | Formula-driven total